## Sheet1
Device Name | Owner | App/Tool Name | Major category | Environment | Physical / Virtual? | Migrate to AWS? | R Rating | Wave | Comments | Due Date | Status2 | Memory Size (MB) | CPU Architecture | LB | AMI | AMI Id | AWS Account | Tier | AZ | VPC Id | Subnet Id | Subnet Name | Subnet CIDR
NAIDCACS | Jai Sue | ACS | Security | Prod | Virtual | n | retain |  |  |  |  | 4096
APPUSSECADM01PD | Jai Sue | Active Admin |  | Prod | Virtual | ? |  |  | Research with Alan Mong , replacement in progress |  |  | 8192
NAIDCADFS | Ryan Jacobs | ADFS | AD | Prod | Virtual | y | replatform | 1 | mehmet to implement |  |  | 4096
NAIDCADFS3n1 | Ryan Jacobs | ADFS | AD | Prod | Virtual | y | replatform | 1 | mehmet to implement |  |  | 8192
NAIDCADFS3n2 | Ryan Jacobs | ADFS | AD | Prod | Virtual | y | replatform | 1 | mehmet to implement |  |  | 8192
NAIDCADFSMOB | Ryan Jacobs | ADFS | AD | Prod | Virtual | y | replatform | 1 | mehmet to implement |  |  | 8192
NAIDCADFSMOB2 | Ryan Jacobs | ADFS | AD | Prod | Virtual | y | replatform | 1 | mehmet to implement |  |  | 8192
phd-adtraq | Shawn Burk | Adtraq | Media Tool |  | Virtual | [6 empty] | 3072
NAIDCALTERYX | Wayne Kramer | Alteryx | Media Tool |  | Virtual | y | rehost |  | rehost due to concerns about ODBC connections |  |  | 32768
NAIDCAMP | Jai Sue | AMP | Media Tool |  | Virtual | ? | [5 empty] | 8192
ANLCTCOGAS1 | John Briscoe | Annalect | Media Tool |  | Virtual | [6 empty] | 32768
ANLCTMSPJS1 | John Briscoe | Annalect | Media Tool |  | Virtual | [6 empty] | 8192
naidcanlctiflour | John Briscoe | Annalect | Media Tool |  | Virtual | [6 empty] | 4096
AWSUSSECGVT01PD | Jai Sue | AWS Storage Gateway |  | Prod | Virtual | n | retain |  | do we need post cognos |  |  | 7960
AWSUSSECSVG01PD | Jai Sue | AWS Storage Gateway |  | Prod | Virtual | n | retain |  |  |  |  | 16384
NAIDCAXDEV1v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  | pending discussion with anu |  |  | 20480
NAIDCAXDEV2-1v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXDEV2v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXDEV3v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXDEV4v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXDEV5v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXDEV6v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXDEV7v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXDEV8v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXDEVSQL1 | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 32768
NAIDCAXDMAOS1v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAX-DMAOS2v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXMON | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXSQL1N1 | Anu Hume | Axapta | SQL Server |  | Physical |  | retain |  |  |  |  | 262144 | Intel Xeon
NAIDCAXSQL2v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 32768
NAIDCAXSSRS1v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXTERM1v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXTST1v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCAXTST2v | Anu Hume | Axapta | Finance |  | Virtual |  | retain |  |  |  |  | 20480
NAIDCBDEFP | Harry Robinson | ScreenPlay and Omnet EDI | Media Tool |  | Virtual | [6 empty] | 4096
NAIDCROOTCA | Ryan Jacobs | Certs | Security |  | Virtual | ? | research |  | ryan to research |  |  | 4096
CTXUSSECLIC01PD | Jai Sue | Citrix (License Server) | Citrix | Prod | Virtual | y | rehost |  |  |  |  | 8192
CTXUSSECXDC02PD | Jai Sue | Citrix DCs | Citrix | Prod | Virtual | y | rehost |  |  |  |  | 8192
CTXUSSECXDC01PD | Jai Sue | Citrix DCs | Citrix | Prod | Virtual | y | rehost |  |  |  |  | 8192
CTXUSSECAPP00PD | Jai Sue | Citrix MCS | Citrix | Prod | Virtual | y | rehost |  |  |  |  | 24576
CTXUSSECSFT02PD | Jai Sue | Citrix StoreFront | Citrix | Prod | Virtual | y | rehost |  |  |  |  | 8192
CTXUSSECSFT01PD | Jai Sue | Citrix StoreFront | Citrix | Prod | Virtual | y | rehost |  |  |  |  | 8192
CTXUSSECFLS01PD | Jai Sue | Citrix File Server | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 8192
CTXUSSECDSK06PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECDSK05PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECDSK04PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECDSK03PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECDSK02PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECDSK01PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECDSK00PD | Jai Sue | Citrix MCS | Citrix | Prod | Virtual | y | rehost |  |  |  |  | 24576
CTXUSSECAPP10PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform
CTXUSSECAPP09PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform
CTXUSSECAPP08PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform
CTXUSSECAPP07PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECAPP06PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECAPP05PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECAPP04PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECAPP03PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECAPP02PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
CTXUSSECAPP01PD | Jai Sue | Citrix VDA | Citrix | Prod | Virtual | y | replatform |  |  |  |  | 24576
NAIDCClearPass01 | Jai Sue | ClearPass | IAM | Prod | Virtual | n | retain |  |  |  |  | 24576
naidccode42 | Julia Goodwin | Crash Plan | Development |  | Virtual | y | rehost |  |  |  |  | 8192
NYCCREAM | ?? | cream | Media Tool |  | Virtual | [6 empty] | 4096
NA-US-IDC1.omd.com | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 4096
NA-US-IDC10 | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 8192
NA-US-IDC11 | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 4096
NA-US-IDC12 | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 8192
NA-US-IDC12-SB | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 4096
NA-US-IDC13.omd.com | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 4096
NA-US-IDC2.omd.com | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 4096
NA-US-IDC3 | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 6144
NA-US-IDC4 | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 8192
NA-US-IDC7.extnet.ext | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 4096
NA-US-IDC8.extnet.ext | Ryan Jacobs | dc | AD | prod | Virtual | y | refactor | 1 |  |  | WIP | 4096
NAIDCDHCP2 | Jai Sue | DHCP | Network | Prod | Virtual | y | replatform |  |  |  |  | 4096
NAIDCEFAX | Jai Sue/Corcoran Leary | EFT | Telephony | Prod | Virtual | ? | [5 empty] | 6144
NAIDCEFT | Dan Rowe | EFT | Finance | Prod | Virtual | ? |  |  | feed many systems - 800 gig a month |  |  | 4096
NAIDCEFTGATEWAY | Dan Rowe | EFT |  | Prod | Virtual | ? |  |  | dmz server |  |  | 16384
IISUSIDCEMP01PD | Amir Jatoi | empowerID | IAM | Prod | Virtual | y | rehost |  |  |  |  | 12288
IISUSIDCEMP02PD | Amir Jatoi | empowerID | IAM | Prod | Virtual | y | rehost |  |  |  |  | 12288
NAIDCSQL-EMP-SB | Amir Jatoi | EmpowerID | IAM | staging | Virtual | y | [5 empty] | 12288
APPUSIDCEMP01PD | Amir Jatoi | empowerID | IAM | prod | Virtual | y | rehost |  |  |  |  | 12288
APPUSIDCEMP02PD | Amir Jatoi | empowerID | IAM | prod | Virtual | y | rehost |  |  |  |  | 12288
NAIDCEMPOWERAPP | Amir Jatoi | EmpowerID Test | IAM | staging | Virtual | y | rehost |  |  |  |  | 12288
NAIDCEMPOWERAPP | Amir Jatoi | EmpowerID Test | IAM | staging | Virtual | y | rehost |  |  |  |  | 12288
NAIDCEMPOWERRDP | Amir Jatoi | EmpowerID Test | IAM | staging | Virtual | y | rehost |  |  |  |  | 4096
NAIDCEMPOWERW3 | Amir Jatoi | EmpowerID Test | IAM | staging | Virtual | y | rehost |  |  |  |  | 12288
NAIDCEMPOWERW4 | Amir Jatoi | EmpowerID Test | IAM | staging | Virtual | y | rehost |  |  |  |  | 12288
NAIDCEMPOWERW5 | Amir Jatoi | EmpowerID Test | IAM | staging | Virtual | y | rehost |  |  |  |  | 12288
NAIDCCENTAPP1 | Harry Robinson | Application Server - screenplay, seccon, nervecenter | Collaboration | Prod | Virtual | [6 empty] | 8192
NAIDCITAPP | Harry Robinson | technology financial mgmt system | Collaboration | Prod | Virtual | y | replatform | 1 | other apps on server - research |  |  | 4096
NYCCORPORATE | Jai Sue | FileServe | Collaboration | Prod | Virtual | n | retain |  |  |  |  | 6144
NAIDCCA | Ryan Jacobs | FileServe - certificate authority | Collaboration | Prod | Virtual | y | research |  | ryan to research |  |  | 8192
DSYUSIDCGCD01PD | Ryan Jacobs | Outpost DB |  |  | Virtual | y | replatform | 1 |  |  | WIP | 8192
IISUSNYCIDC01PD | Amir Jatoi | EmpowerID | Web | prod | Virtual | y | rehost |  |  |  |  | 12288
IISUSNYCIDC02PD | Amir Jatoi | EmpowerID | Web | prod | Virtual | y | rehost |  |  |  |  | 12288
NAIDCADMIN | Jai Sue | PGP | Tool |  | Virtual | y | replatform |  | being upgraded |  |  | 8192
NAIDCJSS1 | Adam Latz | Security |  |  | Virtual | [6 empty] | 8192
NAIDCJSS2 | Adam Latz | McAfee EPO |  |  | Virtual | [6 empty] | 8192
IISUSSECK2N01DV | Rajashree Baradur/Harry Robinson | McAfee |  | Dev | Virtual | y | rehost |  |  |  |  | 8192
IISUSSECK2N01PD | Rajashree Baradur/Harry Robinson | McAfee |  | Prod | Virtual | y | rehost |  |  |  |  | 8192
IISUSSECK2N02PD | Rajashree Baradur/Harry Robinson | Varonis |  | Prod | Virtual | y | rehost |  |  |  |  | 8192
NAIDCLIVEACT01 | ?? | Varonis | Collaboration |  | Virtual | [6 empty] | 4096
NAIDCMILDAP |  | Varonis | Security |  | Virtual | [6 empty] | 4096
NMSUSIDCLIV01PD | Jai Sue | Varonis | AD |  | Virtual | [6 empty] | 10240
NAIDCRELAY1 | Marilyn Lopez | relay | Email | prod | Virtual | y | rehost |  |  |  |  | 3072 |  | Y
NAIDCRELAY2 | Marilyn Lopez | relay | Email | prod | Virtual | y | rehost |  |  |  |  | 2048 |  | Y
MIDUSSECSVN01PD | Deb Garrod | Zscaler |  |  | Virtual | n | retain |  |  |  |  | 4096
NAIDCNSFILER02 | Jai Sue | Nasuni Filer |  |  | Virtual | [6 empty] | 8192
NAIDCSNICDEVV | Deb Garrod | NICUS | Security |  | Virtual | y | [5 empty] | 12288
NAIDCSNICPRODV | Deb Garrod | NICUS | Financial |  | Virtual | y | [5 empty] | 12288
NAIDCSNICSTGV | Deb Garrod | NICUS | Financial |  | Virtual | y | [5 empty] | 12288
naidcasnimsoft | Jai Sue | NIM | Tool |  | Virtual | n | retain |  |  |  |  | 8192
DSYUSIDCOKT01PD | Ryan Jacobs | Okta |  |  | Virtual | y | replatform | 1 |  | 2018-10-01 | WIP | 16384
DSYUSIDCOKT01ST | Ryan Jacobs | Okta |  |  | Virtual | y | replatform | 1 |  | 2018-10-01 | WIP | 4096
DSYUSIDCOKT02PD | Ryan Jacobs | Okta |  |  | Virtual | y | replatform | 1 |  | 2018-10-01 | WIP | 16384
nycomd2goweb | ?? | ? | Collaboration |  | Virtual | [6 empty] | 4096
nycweb2.omd.com | Harry Robinson | Original PO system |  | Prod | Virtual | y | rehost | 1 | old PO system - ask deb if we can decomm |  |  | 4096
NAIDCOBAPP1 | Anu Hume/Harry Robinson | onbase production - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NAIDCOBAPP2 | Anu Hume/Harry Robinson | onbase production - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NAIDCOBAPP3 | Anu Hume/Harry Robinson | onbase production, IIS - IT Purchasing Ordering (PO), Media Authorication, Novus Media Accounting, Vendor Inquiry, Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 16384
NAIDCOBCOLD1 | Anu Hume/Harry Robinson | onbase production - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | y | replatform |  |  |  |  | 4096
NAIDCOBFILE | Anu Hume/Harry Robinson | onbase production file server - IT Purchasing Ordering (PO), Nerve Center, Media Authorication, MPSC, Vendor Inquiry, Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 8192
NAIDCOBIDOL | Anu Hume/Harry Robinson | onbase production - IIS - Nerve Center | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NAIDCOBSQLN1 | Anu Hume/Harry Robinson | onbase production - multiple web apps - IT Purchasing Ordering (PO), Media Authorication, MPSC, Nerve Center, OMNET EDI Invoicing, Screenplay (WB), Seccon, Vendor Inquiry, Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | SQL Server | Prod | Physical | Y | replatform |  |  |  |  | 49152 | Intel Xeon
NAIDCOBSQLN2 | Anu Hume/Harry Robinson | onbase production - multiple web apps - IT Purchasing Ordering (PO), Media Authorication, MPSC, Nerve Center, OMNET EDI Invoicing, Screenplay (WB), Seccon, Vendor Inquiry, Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | SQL Server | Prod | Physical | Y | replatform |  |  |  |  | 49152 | Intel Xeon
NAIDCOBSS | Anu Hume/Harry Robinson | onbase - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), IT Purchasing Ordering (PO) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NAIDCOBSS1 | Anu Hume/Harry Robinson | onbase - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), IT Purchasing Ordering (PO) | Finance | Prod | Virtual | y | replatofrm |  |  |  |  | 4096
NAIDCOBVER | Anu Hume/Harry Robinson | onbase - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NAIDCOBVER1 | Anu Hume/Harry Robinson | onbase - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), IT Purchasing Ordering (PO) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NAIDCOBWEB3 | Anu Hume/Harry Robinson | onbase - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 16384
NAIDCOBWEB4 | Anu Hume/Harry Robinson | onbase - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 16384
NAIDCOBWF1 | Anu Hume/Harry Robinson | onbase - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), Media Authorication, IT Purchasing Ordering (PO) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 8192
NAIDCONBASESQL | Anu Hume/Harry Robinson | onbase staging - multiple web apps - IT Purchasing Ordering (PO), Media Authorication, MPSC, Nerve Center, OMNET EDI Invoicing, Screenplay (WB), Seccon, Vendor Inquiry, Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | SQL Server | Prod | Virtual | Y | replatform |  |  |  |  | 24576
NAIDCONETSCRIPT | ?? |  |  | Prod | Virtual | ? | ? |  |  |  |  | 4096
NAIDCSSASDEV | ?? |  |  | Prod | Virtual | ? | ? |  |  |  |  | 32768
NYCOBDEVAPP | Anu Hume/Harry Robinson | onbase test system - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | ? | ? |  | not on claudels list |  |  | 4096
NYCOBFILE2 | Anu Hume/Harry Robinson | onbase - IT Purchasing Ordering (PO), Nerve Center, Media Authorication, MPSC, Vendor Inquiry, Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 1044
NYCOBTESTAPP | Anu Hume/Harry Robinson | onbase test system - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), IT Purchasing Ordering (PO), Media Authorication, Vendor Inquiry, Novus Media Accounting, Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), IT Purchasing | Finance | test | Virtual | Y | replatform |  |  |  |  | 4096
NYCOBTESTFILE | Anu Hume/Harry Robinson | onbase test system - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), IT Purchasing Ordering (PO), Media Authorication, Vendor Inquiry, Novus Media Accounting | Finance | test | Virtual | Y | replatform |  |  |  |  | 4096
NYCOBTESTSS | Anu Hume/Harry Robinson | onbase test system - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), IT Purchasing Ordering (PO) | Finance | test | Virtual | Y | replatform |  |  |  |  | 4096
NYCOBTESTWEB | Anu Hume/Harry Robinson | onbase test system - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL) | Finance | test | Virtual | Y | replatform |  |  |  |  | 4096
NYCOBTESTWF | Anu Hume/Harry Robinson | onbase test system - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), Media Authorication, IT Purchasing Ordering (PO) | Finance | test | Virtual | Y | replatform |  |  |  |  | 4096
NYD-OB7A | Anu Hume/Harry Robinson | Onbase | Financial | Prod | Virtual | y | replatform |  |  |  |  | 4096
NYD-OB7B | Anu Hume/Harry Robinson | onbase production - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), Vendor Inquiry | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NYD-OB7C | Anu Hume/Harry Robinson | onbase production - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), Vendor Inquiry | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NYD-OB7D | Anu Hume/Harry Robinson | onbase production - Media AP Invoicing (OMD,PHD,OMNET,RM, NOVUS, PL), Vendor Inquiry | Finance | Prod | Virtual | Y | replatform |  |  |  |  | 4096
NAIDCOPENNMS1 | Jai Sue | OpenNMS | Tool |  | Virtual | n | retain |  |  |  |  | 10240
NAIDCHIAB1 | Mamani Older | Outpost24 | Security | Prod | Virtual | N | Retain |  | Retain for local resources |  |  | 32768
NAIDCHIAB2 | Mamani Older | Outpost24 | Security | Prod | Virtual | N | Retain |  | Retain for local resources |  |  | 32768
NAIDCHIAB3 | Mamani Older | Outpost24 | Security | Prod | Virtual | N | Retain |  | Retain for local resources |  |  | 32768
NAIDCHIAB4 | Mamani Older | Outpost24 | Security | Prod | Virtual | Y | replatform |  | Scan AWS Servers only |  |  | 32768
NAIDCSPPOC1 | Harry Robinson | Sharepoint development | SharePoint | sandbox | Virtual | y | rehost | 1 |  |  |  | 24576
NAIDCWEB2 | Harry Robinson | Multi web applications | Web | Prod | Virtual | y | replatform |  |  |  |  | 16384
NAIDCWEB3 | Harry Robinson | Multi web applications | Web | Prod | Virtual | y | replatform |  |  |  |  | 16384
NAIDCPPHFT2 | Dan rowe | ProofPoint-AD syncs |  |  | Virtual | y | rehost | 1 | custom linux image |  |  | 8192
NAIDCPPM | ? |  |  |  | Virtual |  | research |  | Not proofpoint per dan/corcoran |  |  | 4096
NAIDCPPTRAP | Dan rowe | ProofPoint-email security |  |  | Virtual | y | rehost | 1 |  |  |  | 8192
NAIDCRAn1 | Ryan Jacobs | ADFS |  |  | Virtual | ? |  |  | older ADFS Servers - Mehmet |  |  | 8192
NAIDCRAn2 | Ryan Jacobs | ADFS |  |  | Virtual | ? |  |  | older ADFS Servers - Mehmet |  |  | 8192
NAIDCEXCHANGE | Marilyn Lopez | Relay | File Transfer | prod | Virtual | y | rehost |  |  |  |  | 16384
NAIDCRESEARCH | Jon Serrete | Research | Media Tool |  | Virtual | [6 empty] | 4096
NAIDCSCCM1 | Jai Sue | SCCM | Monitoring |  | Virtual | [6 empty] | 16384
NAIDCSCCM2 | Jai Sue | SCCM | Monitoring |  | Virtual | [6 empty] | 4096
NAIDCSCCMDP01 | Jai Sue | SCCM | Monitoring |  | Virtual | [6 empty] | 8192
NAIDCSCCMRPT | Jai Sue | SCCM | Monitoring |  | Virtual | [6 empty] | 8192
NAIDCEPF1 | ? | Security | Security |  | Virtual |  | research |  |  |  |  | 8192
NAIDCETM | Mamani Older | SIEM DB | Antivirus | Prod | Physical | N |  |  | Review strategy with OMC |  |  | 12288
NAIDCSM | Jai Sue | Solarwinds | Monitoring |  | Virtual | [6 empty] | 16384
naidcsm2 | Jai Sue | Solarwinds | Monitoring |  | Virtual | [6 empty] | 8192
naidcsm3 | Jai Sue | Solarwinds | Monitoring |  | Virtual | [6 empty] | 4096
NAIDCSMDW | Jai Sue | Solarwinds | Monitoring |  | Virtual | [6 empty] | 16384
PHDNY-PROD-SL | Anu Hume | Solomon | Finance |  | Virtual | y | rehost |  |  |  |  | 4096
phdny-db01 | Anu Hume | Solomon SQL | SQL Server |  | Virtual | y | rehost |  |  |  |  | 8192
NAIDCSPSS | Jon Serrete | SPSS | Media Tool |  | Virtual | [6 empty] | 4096
NAIDCSQLNODE1 | Damien Lennark/Jai | SQL ActiveAdministrator / VMWare | SQL Server | Prod | Physical | [6 empty] | 49152 | Intel Xeon
NAIDCSQLNODE2 | Damien Lennark/Jai | SQL ActiveAdministrator / VMWare | SQL Server | Prod | Physical | [6 empty] | 49152 | Intel Xeon
NAIDCPRDSSAS | Harry Robinson/Damien | SSAS | ETL | Prod | Virtual |  |  |  | ETL server |  |  | 32768
NAIDCAPPSTG1 | Harry Robinson | Multi web applications |  | staging | Virtual | y | replatform |  |  |  |  | 8192
NAIDCNetSUS1 | Jai Sue | SUS | Patch Mgmt |  | Virtual | [6 empty] | 2048
APPUSSECSYM01PD | Jon Serette | Symprex |  |  | Virtual | [6 empty] | 8192
NAIDCSYMPREX | Jon Serrete | Symprex | Collaboration |  | Virtual | [6 empty] | 4096
NAIDCTALEOTCC | Jon Serrete | Taleo | HR |  | Virtual | [6 empty] | 4096
IDCWIN7 | Jai Sue | TestVM |  |  | Virtual | [6 empty] | 4096
NAIDCTFS | Harry Robinson | source code repository - tfs | source | Prod | Virtual | y | rehost | 1 |  |  |  | 8192
NAIDCTMS01 | John Atalla | TMS | Media Tool |  | Virtual | y | [5 empty] | 4096
NAIDCTSCAL | Jai Sue | TMV | Terminal Services |  | Virtual | [6 empty] | 6144
NAIDCTSG2 | Jai Sue | TMV | Terminal Services |  | Virtual | [6 empty] | 4096
NAIDCUNIFLOW01 | Corcoran Leary | Uniflow | Printing |  | Virtual | y | rehost | 1 |  |  |  | 8192
APPUSSECVAR04PD | Mamani Older | Varonis- IDU | Security | Prod | Virtual | ? | [5 empty] | 32768
APPUSSECVAR05PD | Mamani Older | Varonis-NA Collector | Security | Prod | Virtual | ? | [5 empty] | 16384
APPUSSECVAR06PD | Mamani Older | Varonis-NA Collector | Security | Prod | Virtual | ? | [5 empty] | 16384
APPUSSECVAR07PD | Mamani Older | Varonis-NA Collector | Security | Prod | Virtual | ? | [5 empty] | 16384
APPUSSECWR201PD | Mamani Older | Varonis | Security | Prod | Virtual | ? | [5 empty] | 4096
NAIDCVARONIS3 | Mamani Older | Varonis | Security | Prod | Virtual | ? | [5 empty] | 8192
SQLUSIDCVAR01PD | Mamani Older | Varonis-NA Collector | Security | Prod | Virtual | ? | [5 empty] | 131072
NAIDCVCENTER | Jai Sue | Vcenter | Tool |  | Virtual | y | [5 empty] | 16384
naidcvcorch1 | Jai Sue | Vcenter | Tool |  | Virtual | y | [5 empty] | 4096
NAIDCVSA | Jai Sue | Vcenter | Tool |  | Virtual | y | [5 empty] | 4096
naidcbackup10 | Jai Sue | Veritas | Backup |  | Virtual | n | [5 empty] | 4096
CiscoUnity1_B | Jai Sue | Voicemail | Telephony |  | Virtual | n | [5 empty] | 6144
CiscoUnity2 | Jai Sue | Voicemail | Telephony |  | Virtual | n | [5 empty] | 6144
NAIDCUCM9PUB | Jai Sue | VoIP | Telephony |  | Virtual | n | [5 empty] | 6144
NAIDCUCM9SUB1 | Jai Sue | VoIP | Telephony |  | Virtual | n | [5 empty] | 6144
NAIDCUCM9SUB2 | Jai Sue | VoIP | Telephony |  | Virtual | n | [5 empty] | 6144
NAIDCUEAC-CUCM9 | Jai Sue | VoIP | Telephony |  | Virtual | n | [5 empty] | 4096
NAIDCUSYNC | Jai Sue/Rayn Jacobs | VoIP | Telephony |  | Virtual | y | replatform | 2 | coordinate with OMC |  |  | 4096
NAIDCWPMYSQL | Rajashree Baradur | WordPress | Media Tool |  | Virtual | y | replatform |  |  |  |  | 2048
NAIDCWPPROD1 | Rajashree Baradur | WordPress | Media Tool |  | Virtual | y | replatform |  |  |  |  | 16384
NAIDCWPPROD2 | Rajashree Baradur | WordPress | Media Tool |  | Virtual | y | replatform |  |  |  |  | 16384
NAIDCZSNSS1 | Mamani Older | Zscaler | Security | Prod | Virtual | N | retain |  | High I/O |  |  | 8192
IISUSSECEXC01PD | Marilyn Lopez |  |  | Test | Virtual | y | rehost |  |  |  |  | 4096
NAIDCBACKUPAWS | Jai Sue |  |  |  | Virtual | [6 empty] | 4096
naidcsmcipher01 | Damien Lennark |  | Infrastructure |  | Virtual | [6 empty] | 4096
NA-US-IDC7-SB | Jai Sue |  |  |  | Virtual | ? | [5 empty] | 8192
NYD-OB7E | Anu Hume/Harry Robinson | onbase | Finance | Prod | Virtual | y | replatform |  |  |  |  | 4096
NYD-OB7F | Anu Hume/Harry Robinson | onbase | Finance | Prod | Virtual | y | replatform |  |  |  |  | 8192
NYD-OB7G | Anu Hume/Harry Robinson | onbase | Finance | Prod | Virtual | Y | replatofrm |  |  |  |  | 8192
PORCENTRAL | Jai Sue |  | file server |  | Virtual | n |  |  | Portland file server |  |  | 4096
Sandbox FW | Jai Sue |  |  |  | Virtual | n |  |  | move to harborside |  |  | 2048
SIMUSSECO2401PD | Mamani Older | Sophos Event Proxy | Security | Prod | Virtual | N | retain |  | High I/O |  |  | 8192
SQLUSIDCEMP01PD | Amir Jatoi | EmpowerID, Symprex, Other Ops DBs |  | Prod | Virtual | y |  |  | any issues with extnet |  |  | 65536
SQLUSIDCEMP02PD | Amir Jatoi | EmpowerID, Symprex, Other Ops DBs |  | Prod | Virtual | y | [5 empty] | 65536
StruxureWare Data Center Expert |  |  |  |  | Virtual | n | retain |  |  |  |  | 1024